## Base
Project Title: | Software Project
Start Date: | 2014-05-19
Estimated Completion Date: | 2014-06-04
TaskID | Task | 2019-05-20 |  |  | 2019-05-21 |  |  | 2019-05-22 | 2019-05-23 | 2019-05-24 | 2019-05-25 | 2019-05-26 | 2019-05-27 | 2019-05-28 | 2019-05-29 | 2019-05-30 | 2019-05-31 | 2019-06-01 | 2019-06-02 | 2019-06-03 | 2019-06-04 | 2019-06-05
|  | 0900 | 1200 | 1500 | 0900 | 1200 | 1500 | 2019-06-05: 1500
1.1 | Initial Meeting with Client to Define User Requirements
1.2 | Write draft SRS document
1.3 | Design Draft User Interface
1.4 | Email draft to Client for comment
1.5 | Make changes to draft
1.6 | Meet with client to sign contract
2 | Design User Interface
3 | Code Program | [6 empty] | 2019-05-24: SICK; 2019-05-29: SICK; 2019-05-30: SICK; 2019-05-31: SICK
4 | Hire contractor induct to project and finalise contract | bar: 2019-05-24
5 | Write Draft Documentation | bar: 2019-05-24; 2019-05-27 to 2019-05-29
6 | Test Application | bar: 2019-06-03
7 | Finalise Documentation | bar: 2019-06-04
8 | Deliver to Client for Signoff | bar: 2019-06-05
Resources
Project Manager
User Interface Designer
Programmer
Technical Writer
Client
Contractor